## Slide 1: Class 2Nx2NB Group 322 SPRINT 1
Group members:
Diogo Santo (1212039)
Paulo Moreira (1212044)
Rafael Carolo (1212047)
Ricardo Gonçalves (1221720)
Tassio Gomes (1170065) (BDDAD)

## Slide 2: Sprint planning – Sprint 1
SPRINT BACKLOG | 
Number of stories | 11
Number of bugs | 0
Number of tasks | 11
Number of Management Tasks | 16
Number of team members | Planned: 5 Actual: 5
Total planned estimation vs execution | Planned hours: 95 Executed hours: 95
Planned Start Date: 01-10-2023 Real Start Date: 06-10-203
Planned Finished Date: 29-10-2023 Real Finish Date: 29-10-2023

## Slide 3: Sprint planning
Assignment US | Commited? | Todo | Doing | Testing | Done | Blocked
US LP01 | 06-10-2023 |  |  |  | X | 
US LP02 | 06-10-2023 |  |  |  | X | 
US BD01 | 06-10-2023 |  |  |  | X | 
US BD02 | 06-10-2023 |  |  |  | X | 
US BD03 | 06-10-2023 |  |  |  | X | 
US BD04 | 06-10-2023 |  |  |  | X | 
US BD05 | 06-10-2023 |  |  |  | X | 
US BD06 | 06-10-2023 |  |  |  | X | 
US BD07 | 06-10-2023 |  |  |  | X | 
US BD08 | 06-10-2023 |  |  |  | X | 
US BD09 | 06-10-2023 |  |  |  | X | 

## Slide 4: Work by team member
Chart: Hours / n. tasks
| Diogo Santo | Paulo Moreira | Rafael Carolo | Ricardo Gonçalves | Tassio Gomes
Horas / tarefas | 18.35 | 16.18 | 16.18 | 18.35 | 11.93

## Slide 5: Work by type
Chart: Componente
| ESINF | ARQCP | BBDAD | LAPR3 | FSIAP
Componente | 0 | 0 | 9 | 2 | 0

## Slide 6: Sprint Burndown Chart

## Slide 7: Sprint Retrospective
Date: 29-10-2023
What went well?
Communication
Tasks organization and inter support
What went wrong?
Initialization of sprint on JIRA.
What we’ve learned?
Set up all the work hours / points before sprint start on JIRA.

## Slide 8: Sprint Retrospective
Date: 29-10-2023
Action items:
Set up all the work hours / points before sprint 2 start, on JIRA.
Close sprint on JIRA.
Submit all documents on each required platform.